## Momen
Bug ID | Bug describtion | Steps to reproduce | Expected result | Actual Result | Attachments | Environment | severity | Priority
bug_automation_Exercise_01 | in (search_product with value )request , when enter more than one category to search_product, the response is empty with status code 200 | 1- open postman 2- open automation_exercise collection 3- open "post to search_product" request 4-enter two categories to search_product data field in pstman data form 5- send the request 6- check the response | the response should include response code 200 with data related to entered categories | the request results "response code 200 with empty data | https://drive.google.com/file/d/12y2tab9KAHULevCfrFx2eOmhUZD2VpkW/view?usp=sharing | windos11, (google chrome) | low | low
bug_automation_Exercise_02 | in (search_product with value ) request, when let the search_product empty, the request returns response code 200 with all data | 1- open postman 2- open automation_exercise collection 3- open "post to search_product" request 4-let search_product data field empty 5- send the request 6- check the response | " responseCode: 400, "message: Bad request, search_product parameter is missing in POST request" | the request returns response code 200 with all products data | https://drive.google.com/file/d/1xjLERGOvMDShq_Cmo6qkkZ_glKrrnvG1/view?usp=sharing | windos11, (google chrome) | low | low
bug_automation_Exercise_03 | in (create_user) request, there is no restrictions on all fields, fields accept invalid data( including spaces) and returns response ""responseCode": 201, "message": "User created!"" | 1- open postman 2- open automation_exercise collection 3- open "create_user_account" request 4- enter invalid values to the body parameters 5- send the request 6- check the response | the response ahould include status code 400 with error message " invalid values" | the request returns "responseCode": 201, "message": "User created!" | https://drive.google.com/file/d/1RCcIksKPIQf-uLJe1aAotCB3m-s8MzY3/view?usp=sharing | windos11, (google chrome) | high | high
bug_automation_Exercise_04 | in (create_user) request, when you let the fields empty, the response message is " responseCode": 400, "message": "Email already exists!" | 1- open postman 2- open automation_exercise collection 3- open "create_user_account" request 4- let all body parameters empty 5- send the request 6- check the response | the response ahould include status code 400 with error message " invalid values" | the response message is " responseCode": 400, "message": "Email already exists!" | https://drive.google.com/file/d/185tN8EG53aeFPDZ_ZhRb8zWatQEQT4EA/view?usp=sharing | windos11, (google chrome) | low | low
bug_automation_Exercise_06 | in (update_user) request, there is no restrictions on the fields, fields accept invalid (including spaces) data and update user details with reponse "responseCode": 200, "message": "User updated!" | 1- open postman 2- open automation_exercise collection 3- open "update_user_account" request 4- enter invalid values to body parameteres 5- send the request 6- check the response | the response ahould include status code 400 with error message " invalid values" | fields accept all kinds of data and update user details with reponse "responseCode": 200, "message": "User updated!" | https://drive.google.com/file/d/1E2oIANQEwxrZqcYfJ8s176GbJCLaAmRC/view?usp=sharing | windos11, (google chrome) | high | high
bug_automation_Exercise_07 | in (update_user) request, when you update fields with empty data, fields accept these values and update user details with reponse "responseCode": 200, "message": "User updated!" | 1- open postman 2- open automation_exercise collection 3- open "update_user_account" request 4- let body parameteres empty 5- send the request 6- check the response | the response ahould include status code 400 with error message " invalid values" | fields accept these values and update user details with reponse "responseCode": 200, "message": "User updated!" | https://drive.google.com/file/d/16IhEX4C4zANY2NpeImrS_MiAaIJkLkqO/view?usp=sharing | windos11, (google chrome) | low | low
bug_automation_Exercise_08 | in (get_user_details) request, when you let the email field empty, it responses with details of a user | 1- open postman 2- open automation_exercise collection 3- open "get_user_detailst" request 4- let email parameter empty 5- send the request 6- check the response | the response ahould include status code 400 with error message "please enter valid email" | request returns response code 200 with details of a user | https://drive.google.com/file/d/1Oe9Fat-UPaLRNOhiZZmYFYJ_F8JMPLZD/view?usp=sharing | windos11, (google chrome) | high | high
bug_automation_Exercise_09 | in (get_user_details) request, the email data filter accepts non email values | 1- open postman 2- open automation_exercise collection 3- open (create_user) req 4- create user with invalid email 5- open "get_user_detailst" request 6- lenter to the parameter the invalid email we entered before 7- send the request 8- check the response | the response ahould include status code 400 with error message "please enter valid email" | request returns response code 200 with details of the user | https://drive.google.com/file/d/1r2lLj-dQGVV6lPM2VWuRUWeYPmccFvY8/view?usp=sharing | windos11, (google chrome) | low | low